## Read Me
First 100 videos: production backlog
Built 2026-10-22 from the open-textbook tables of contents (Hefferon, Trench, Lebl, OpenIntro, Grinstead & Snell, Downey) and the YouTube channel scan of 112 channels / 10,339 videos.
Tabs
Backlog: all 100 videos in suggested production order. Edit the Status and Publish date columns as you go; the counts on the Progress tab update automatically.
Schedule: the same 100 videos laid out at 3 per week (34 weeks), with the phase each week belongs to.
By Course: the backlog regrouped by course in textbook (playlist) order, so each playlist reads in prerequisite order.
Progress: live counts by status, course and demand signal.
Columns
Code: LA = Linear Algebra, DE = Differential Equations, PS = Probability & Statistics, XC = cross-course format experiments. The number is the textbook/playlist order within the course.
Source section: the textbook section that is the source of truth for definitions, notation and the worked example. Narration is written fresh from it.
Format: Explainer (6-15 min single concept) / Anchor ("ALL of X in N minutes", made after the explainers exist) / 5 levels / History of an idea.
Demand signal: see the two outlier columns; Low topics stay on the list because the course needs them as prerequisites.
Comparable videos / Small-channel outliers (raw): how many scanned videos match the topic, and how many of those on channels under 150k subs beat 1x their subscriber count with 10k+ views.
Small-channel outliers (age-adj): same test but on views PER YEAR (views divided by the video's age), videos at least 6 months old. This removes the advantage of 10-15 year old videos that accumulated views slowly.
Demand signal is High only when BOTH the raw and the age-adjusted tests pass; Medium when one passes; Low when neither does.
Best evidence: the single scanned video that best shows the topic pulls viewers beyond its channel - watch it before scripting yours.
Prerequisites: codes that should be published first (or an assumed background course).
How the order was chosen
Weeks 1-8 alternate Linear Algebra and Differential Equations in textbook order, so both playlists grow in prerequisite order. Week 9 records the Linear Algebra anchor from the first 12 LA explainers; week 13 the DE anchor. From week 13 the Statistics lane opens and alternates with the remaining LA/DE topics. Format experiments (5 levels, history) sit right after the topic they depend on.

## Backlog
Order | Week | Code | Course | Playlist # | Source section (textbook) | Working title | Format | Target length | Prerequisites | Demand signal | Comparable videos | Small-channel outliers (raw) | Small-channel outliers (age-adj) | Best evidence: video | Evidence channel | Evidence subs | Evidence views | Views / subs | Evidence age (yrs) | Views / yr | Views/yr / subs | Evidence URL | Status | Publish date | Notes | Pending rank (helper)
1 | 1 | LA-01 | Linear Algebra | 1 | Hefferon, Linear Algebra §1.I.1 Gauss's Method | What a system of linear equations really is (and why 3 pictures beat 3 formulas) | Explainer | 6-8 min | None | High | 112 | 18 | 4 | Gaussian elimination ¦ Lecture 10 ¦ Matrix Algebra for Engineers | Jeffrey Chasnov | 102000 | 489000 | 4.7941 | 8 | 61125 | 0.59926 | https://youtu.be/RgnWMBpQPXk | Planned |  |  | 1
2 | 1 | DE-01 | Differential Equations | 1 | Trench, Elementary Differential Equations §1.2 Basic Concepts | What is a differential equation? (and why physics is written in them) | Explainer | 6-8 min | Calculus 1 | Medium | 4 | 1 | 0 | ODE ¦ What is a differential equation? | commutant | 43100 | 318000 | 7.3782 | 14 | 22714.2857 | 0.52701 | https://youtu.be/HKvP2ESjJbA | Planned |  |  | 2
3 | 1 | LA-02 | Linear Algebra | 2 | Hefferon, Linear Algebra §1.I.1 Gauss's Method | Gaussian elimination: the algorithm, visualised row by row | Explainer | 8-10 min | LA-01 | Medium | 29 | 7 | 1 | Elementary Linear Algebra: Echelon Form of a Matrix, Part 1 | James Hamblin | 41900 | 312000 | 7.4463 | 14 | 22285.7143 | 0.53188 | https://youtu.be/wY4TAheBsj4 | Planned |  |  | 3
4 | 2 | DE-02 | Differential Equations | 2 | Trench, Elementary Differential Equations §1.3 Direction Fields | Slope fields: seeing every solution at once | Explainer | 8-10 min | DE-01 | Medium | 6 | 2 | 0 | ODE ¦ Slope fields | commutant | 43100 | 64000 | 1.4849 | 14 | 4571.4286 | 0.10607 | https://youtu.be/MI2xCwBekX4 | Planned |  |  | 4
5 | 2 | LA-03 | Linear Algebra | 3 | Hefferon, Linear Algebra §1.III Reduced Echelon Form | Row echelon form explained: what the zeros are telling you | Explainer | 6-8 min | LA-02 | Medium | 14 | 4 | 0 | Elementary Linear Algebra: Echelon Form of a Matrix, Part 1 | James Hamblin | 41900 | 312000 | 7.4463 | 14 | 22285.7143 | 0.53188 | https://youtu.be/wY4TAheBsj4 | Planned |  |  | 5
6 | 2 | DE-03 | Differential Equations | 3 | Trench, Elementary Differential Equations §2.2 Separable Equations | Separable equations: the first trick everyone learns, explained properly | Explainer | 8-10 min | DE-01 | Low | 3 | 0 | 0 | Differential Equations: Non-linear first order separable equations | MathMeUp | 1750 | 678 | 0.38743 | 6 | 113 | 0.064571 | https://youtu.be/CK_U4OrXiXI | Planned |  |  | 6
7 | 3 | LA-04 | Linear Algebra | 4 | Hefferon, Linear Algebra §1.I.3 General = Particular + Homogeneous | Why solution sets are lines, planes and points (particular + homogeneous) | Explainer | 6-8 min | LA-03 | Low | 16 | 0 | 0 | Linear Algebra - Lecture 28 - Null Space of a Matrix | James Hamblin | 41900 | 30000 | 0.71599 | 5 | 6000 | 0.1432 | https://youtu.be/1b857qTFTgw | Planned |  |  | 7
8 | 3 | DE-04 | Differential Equations | 4 | Trench, Elementary Differential Equations §2.1 Linear First Order | Integrating factors: where that mysterious e^∫p comes from | Explainer | 8-10 min | DE-03 | Medium | 16 | 1 | 0 | ODE ¦ Integrating factors general method | commutant | 43100 | 48000 | 1.1137 | 14 | 3428.5714 | 0.079549 | https://youtu.be/GIpOcHNK7eQ | Planned |  |  | 8
9 | 3 | LA-05 | Linear Algebra | 5 | Hefferon, Linear Algebra §1.II Linear Geometry of n-Space | Vectors are not arrows: three ways to think about a vector | Explainer | 6-8 min | None | Low | 6 | 0 | 0 | Vector Calculus 1: What Is a Vector? | MathTheBeautiful | 98800 | 26000 | 0.26316 | 8 | 3250 | 0.032895 | https://youtu.be/Zx6bizDdkRE | Planned |  |  | 9
10 | 4 | DE-05 | Differential Equations | 5 | Trench, Elementary Differential Equations §2.3 Existence and Uniqueness | Existence and uniqueness, intuitively: when does a DE have one answer? | Explainer | 8-10 min | DE-02 | Medium | 11 | 3 | 0 | ODE ¦ Existence and uniqueness idea | commutant | 43100 | 370000 | 8.5847 | 14 | 26428.5714 | 0.61319 | https://youtu.be/53BPf9JrFcU | Planned |  |  | 10
11 | 4 | LA-06 | Linear Algebra | 6 | Hefferon, Linear Algebra §1.II.2 Length and Angle Measures | The dot product explained visually (projection, angle, work) | Explainer | 8-10 min | LA-05 | Medium | 32 | 1 | 0 | Introducing the Inner Product - A Fundamental Concept in Linear Algebra | MathTheBeautiful | 98800 | 175000 | 1.7713 | 9 | 19444.4444 | 0.19681 | https://youtu.be/Ww_aQqWZhz8 | Planned |  |  | 11
12 | 4 | DE-06 | Differential Equations | 6 | Trench, Elementary Differential Equations §2.5 Exact Equations | Exact equations and the hidden potential function | Explainer | 8-10 min | DE-04 | Low | 2 | 0 | 0 | Exact Differential Equations | MathMeUp | 1750 | 159 | 0.090857 | 6 | 26.5 | 0.015143 | https://youtu.be/Ii_MCo6RodA | Planned |  |  | 12
13 | 5 | LA-07 | Linear Algebra | 7 | Hefferon, Linear Algebra §3.IV.2 Matrix Multiplication | What a matrix really does: matrices as transformations | Explainer | 8-10 min | LA-05 | High | 39 | 8 | 0 | Matrices Explained Visually — The Hidden Geometry Behind Every Matrix! | Mathspark8 | 7140 | 45000 | 6.3025 | 0.25 | 180000 | 25.2101 | https://youtu.be/qt9LlujnLAs | Planned |  |  | 13
14 | 5 | DE-07 | Differential Equations | 7 | Trench, Elementary Differential Equations §4.1 Growth and Decay | Exponential growth and decay: the DE behind every population curve | Explainer | 6-8 min | DE-03 | Medium | 19 | 1 | 0 | ODE ¦ Population models | commutant | 43100 | 56000 | 1.2993 | 14 | 4000 | 0.092807 | https://youtu.be/gtCswEF3bho | Planned |  |  | 14
15 | 5 | LA-08 | Linear Algebra | 8 | Hefferon, Linear Algebra §3.IV.2 Matrix Multiplication | Why matrix multiplication is defined like that | Explainer | 8-10 min | LA-07 | Low | 6 | 0 | 0 | Matrix Multiplication Properties PROVED ¦ FREE Linear Algebra Course | Mathematics Flipped | 1330 | 707 | 0.53158 | 5 | 141.4 | 0.10632 | https://youtu.be/OcznDjdY46k | Planned |  |  | 15
16 | 6 | DE-08 | Differential Equations | 8 | Trench, Elementary Differential Equations §4.2 Cooling and Mixing | Newton's law of cooling and the mixing-tank problem, animated | Explainer | 8-10 min | DE-04 | Medium | 10 | 2 | 0 | ODE ¦ A model for mixing problems | commutant | 43100 | 115000 | 2.6682 | 14 | 8214.2857 | 0.19059 | https://youtu.be/-Fd6Ates4Gs | Planned |  |  | 16
17 | 6 | LA-09 | Linear Algebra | 9 | Hefferon, Linear Algebra §2.I.2 Subspaces and Spanning Sets | Span: everywhere your vectors can reach | Explainer | 6-8 min | LA-05 | Medium | 26 | 4 | 2 | Linear Algebra Example: Span Questions | James Hamblin | 41900 | 283000 | 6.7542 | 5 | 56600 | 1.3508 | https://youtu.be/OpcznwRgUaY | Planned |  |  | 17
18 | 6 | DE-09 | Differential Equations | 9 | Trench, Elementary Differential Equations §4.4 Autonomous Second Order / Lebl, Notes on Diffy Qs §1.6 | The phase line: stability without solving anything | Explainer | 8-10 min | DE-02 | Medium | 19 | 1 | 0 | Fixed points and stability of a nonlinear system | Jeffrey Chasnov | 102000 | 118000 | 1.1569 | 12 | 9833.3333 | 0.096405 | https://youtu.be/H4fwoVUltl4 | Planned |  |  | 18
19 | 7 | LA-10 | Linear Algebra | 10 | Hefferon, Linear Algebra §2.II Linear Independence | Linear independence: when is a vector redundant? | Explainer | 6-8 min | LA-09 | Medium | 17 | 2 | 1 | Spanning, Linear Independence and Bases - Linear Algebra | Infinium | 2210 | 11000 | 4.9774 | 4 | 2750 | 1.2443 | https://youtu.be/qDnBvZOfFrs | Planned |  |  | 19
20 | 7 | DE-10 | Differential Equations | 10 | Trench, Elementary Differential Equations §3.1-3.3 Numerical Methods | Euler's method to Runge-Kutta: how computers solve DEs | Explainer | 10-12 min | DE-02 | Medium | 8 | 1 | 0 | Runge Kutta Methods ¦ Lecture 50 ¦ Numerical Methods for Engineers | Jeffrey Chasnov | 102000 | 117000 | 1.1471 | 5 | 23400 | 0.22941 | https://youtu.be/C4UymmEi3Kw | Planned |  |  | 20
21 | 7 | LA-11 | Linear Algebra | 11 | Hefferon, Linear Algebra §2.III Basis and Dimension | Basis and dimension: choosing your coordinate system | Explainer | 8-10 min | LA-10 | Medium | 31 | 2 | 0 | Tensor Calculus 3a: The Covariant Basis | MathTheBeautiful | 98800 | 125000 | 1.2652 | 12 | 10416.6667 | 0.10543 | https://youtu.be/rtEk1at3sVk | Planned |  |  | 21
22 | 8 | DE-11 | Differential Equations | 11 | Trench, Elementary Differential Equations §5.1 Homogeneous Linear Equations | Second-order linear DEs: why solutions form a 2D space | Explainer | 8-10 min | DE-04, LA-11 | Medium | 11 | 2 | 0 | ODE ¦ Initial value problems for second order equations | commutant | 43100 | 91000 | 2.1114 | 13 | 7000 | 0.16241 | https://youtu.be/FmLOWvfF_ww | Planned |  |  | 22
23 | 8 | LA-12 | Linear Algebra | 12 | Hefferon, Linear Algebra §3.II Homomorphisms (rank, nullity) | Rank and nullity: what a matrix destroys and what it keeps | Explainer | 8-10 min | LA-11 | Medium | 43 | 1 | 0 | Linear Algebra - Lecture 32 - Dimension, Rank, and Nullity | James Hamblin | 41900 | 47000 | 1.1217 | 5 | 9400 | 0.22434 | https://youtu.be/XIZxlNvAAjo | Planned |  |  | 23
24 | 8 | DE-12 | Differential Equations | 12 | Trench, Elementary Differential Equations §5.2 Constant Coefficient Homogeneous | The characteristic equation: three cases, three pictures | Explainer | 10-12 min | DE-11 | Low | 12 | 0 | 0 | Introduction to PDEs: Solutions and Auxiliary Conditions | Faculty of Khan | 105000 | 88000 | 0.8381 | 10 | 8800 | 0.08381 | https://youtu.be/Ef3CNDTAuBM | Planned |  |  | 24
25 | 9 | LA-36 | Linear Algebra | 36 | Hefferon (whole book) | ALL of Linear Algebra in 8 minutes | Anchor (ALL of…) | 8 min | LA-01…LA-35 | High | 2 | 1 | 1 | ALL of linear algebra in 7 minutes. | KoothBrush | 11700 | 418000 | 35.7265 | 1 | 418000 | 35.7265 | https://youtu.be/QL4_4GAWvPs | Planned |  |  | 25
26 | 9 | LA-13 | Linear Algebra | 13 | Hefferon, Linear Algebra §3.IV.4 Inverses | The inverse matrix: undoing a transformation (and when you can't) | Explainer | 8-10 min | LA-07 | Medium | 13 | 1 | 0 | Computing inverse matrices using Gaussian elimination ¦ Lecture 12 ¦ Matrix Algebra for Engineers | Jeffrey Chasnov | 102000 | 114000 | 1.1176 | 8 | 14250 | 0.13971 | https://youtu.be/vKBNzM3V-Rc | Planned |  |  | 26
27 | 9 | DE-13 | Differential Equations | 13 | Trench, Elementary Differential Equations §6.1 Spring Problems | The mass on a spring: damping, visualised | Explainer | 10-12 min | DE-12 | Medium | 15 | 1 | 0 | Coupled oscillators ¦ Lecture 46 ¦ Differential Equations for Engineers | Jeffrey Chasnov | 102000 | 133000 | 1.3039 | 7 | 19000 | 0.18627 | https://youtu.be/-pXnfzQfupE | Planned |  |  | 27
28 | 10 | LA-14 | Linear Algebra | 14 | Hefferon, Linear Algebra §4.I-II Determinants | Why is the determinant like that? (area, volume and sign) | Explainer | 10-12 min | LA-07 | High | 38 | 4 | 2 | Why is the determinant like that? | broke math student | 26500 | 251000 | 9.4717 | 2 | 125500 | 4.7358 | https://youtu.be/Sv7VseMsOQc | Planned |  |  | 28
29 | 10 | DE-14 | Differential Equations | 14 | Trench, Elementary Differential Equations §5.3-5.4 Nonhomogeneous / Undetermined Coefficients | Forcing terms and undetermined coefficients: guessing with a method | Explainer | 8-10 min | DE-12 | High | 10 | 2 | 1 | Differential Equations 3: Particular Integral and Complementary Function Method | Infinium | 2210 | 43000 | 19.457 | 5 | 8600 | 3.8914 | https://youtu.be/rYq319AOT9E | Planned |  |  | 29
30 | 10 | LA-15 | Linear Algebra | 15 | Hefferon, Linear Algebra §4.III Laplace's Formula | Cofactor expansion without tears: where the formula comes from | Explainer | 8-10 min | LA-14 | Low | 1 | 0 | 0 | Determinant, Inverse, Minor, Cofactor of any 2x2 or 3x3 Matrix | Brain Station Advanced | 483000 | 36000 | 0.074534 | 1 | 36000 | 0.074534 | https://youtu.be/7R-AIrWfeH8 | Planned |  |  | 30
31 | 11 | DE-15 | Differential Equations | 15 | Trench, Elementary Differential Equations §6.1 Forced Oscillation | Resonance: why bridges and wine glasses break | Explainer | 8-10 min | DE-13 | Low | 0 | 0 | 0 | [9 empty] | Planned |  |  | 31
32 | 11 | LA-16 | Linear Algebra | 16 | Hefferon, Linear Algebra §3.V Change of Basis | Change of basis: the same vector in two languages | Explainer | 10-12 min | LA-11 | Low | 6 | 0 | 0 | Linear Algebra - Lecture 31 - Coordinate Systems | James Hamblin | 41900 | 34000 | 0.81146 | 5 | 6800 | 0.16229 | https://youtu.be/sYkojeGZ_vE | Planned |  |  | 32
33 | 11 | DE-16 | Differential Equations | 16 | Trench, Elementary Differential Equations §5.7 Variation of Parameters | Variation of parameters, demystified | Explainer | 8-10 min | DE-14 | Low | 8 | 0 | 0 | 9: Variation of Parameters - Dissecting Differential Equations | Mu Prime Math | 52900 | 5700 | 0.10775 | 6 | 950 | 0.017958 | https://youtu.be/PMldTftChtQ | Planned |  |  | 33
34 | 12 | LA-17 | Linear Algebra | 17 | Hefferon, Linear Algebra §3.VI.1 Orthogonal Projection | Orthogonal projection: the closest point and why it matters | Explainer | 8-10 min | LA-06 | High | 23 | 4 | 1 | How Do Computers Display 3D on a 2D Screen? (Perspective Projection) | Carl the Person | 3040 | 58000 | 19.0789 | 4 | 14500 | 4.7697 | https://youtu.be/eoXn6nwV694 | Planned |  |  | 34
35 | 12 | DE-17 | Differential Equations | 17 | Trench, Elementary Differential Equations §8.1 Introduction to Laplace Transform | The Laplace transform, visually: what it does to a function | Explainer | 10-12 min | DE-12 | High | 79 | 11 | 1 | Laplace Transform Explained Visually — Why Does Differentiation Become Multiplication? | Mathspark8 | 7140 | 58000 | 8.1232 | 0.25 | 232000 | 32.493 | https://youtu.be/diOh7onaIjA | Planned |  |  | 35
36 | 12 | LA-18 | Linear Algebra | 18 | Hefferon, Linear Algebra §3.VI.2 Gram-Schmidt | Gram-Schmidt in 3D: building an orthonormal basis step by step | Explainer | 8-10 min | LA-17 | High | 29 | 6 | 3 | Gram-Schmidt Process in Space (Step-by-Step 3D Visual) | The Bold Math | 298 | 55000 | 184.5638 | 17 | 3235.2941 | 10.8567 | https://youtu.be/pIy8xqh9sWs | Planned |  |  | 36
37 | 13 | DE-18 | Differential Equations | 18 | Trench, Elementary Differential Equations §8.3 Solution of IVPs | Solving differential equations with Laplace: turning calculus into algebra | Explainer | 10-12 min | DE-17 | Medium | 9 | 0 | 0 | Inverse Laplace Transform Explained Visually — Master Partial Fractions & Every Step! | Mathspark8 | 7140 | 6200 | 0.86835 | 0.25 | 24800 | 3.4734 | https://youtu.be/it4qnGcXals | Planned |  |  | 37
38 | 13 | DE-30 | Differential Equations | 30 | Trench (whole book) | ALL of Differential Equations in 10 minutes | Anchor (ALL of…) | 10 min | DE-01…DE-29 | Low | 1 | 0 | 0 | ALL of differential equations in 11 minutes. | KoothBrush | 11700 | 699 | 0.059744 | 0.25 | 2796 | 0.23897 | https://youtu.be/P1s16tvCLTw | Planned |  |  | 38
39 | 13 | PS-01 | Probability & Statistics | 1 | Grinstead & Snell, Intro to Probability §1.2 Discrete Probability | What probability actually is: three interpretations, one set of rules | Explainer | 8-10 min | None | Low | 2 | 0 | 0 | What is probability? Statistics? ML? AI? | Meerkat Statistics | 12100 | 563 | 0.046529 | 4 | 140.75 | 0.011632 | https://youtu.be/EIrsmnodNOM | Planned |  |  | 39
40 | 14 | LA-19 | Linear Algebra | 19 | Hefferon, Linear Algebra Topic: Line of Best Fit | Least squares explained visually: regression is projection | Explainer | 10-12 min | LA-17 | Medium | 32 | 7 | 1 | GLM Intro - 2 - Least Squares vs. Maximum Likelihood | Meerkat Statistics | 12100 | 79000 | 6.5289 | 6 | 13166.6667 | 1.0882 | https://youtu.be/UdADuHJUX6Q | Planned |  |  | 40
41 | 14 | PS-02 | Probability & Statistics | 2 | Grinstead & Snell, Intro to Probability §4.1 Conditional Probability | Conditional probability: why your intuition fails (and how to fix it) | Explainer | 8-10 min | PS-01 | Medium | 14 | 1 | 1 | All Of Conditional Probability in 30 Minutes | Simple Quant | 9100 | 30000 | 3.2967 | 1 | 30000 | 3.2967 | https://youtu.be/dnGJoOHfDBo | Planned |  |  | 41
42 | 14 | DE-19 | Differential Equations | 19 | Trench, Elementary Differential Equations §8.4-8.5 Unit Step Functions | Step functions and switches: Laplace for piecewise forcing | Explainer | 8-10 min | DE-18 | Low | 5 | 0 | 0 | Intuition: How does the Heaviside Activation Function work? | IntuitiveML | 7800 | 1300 | 0.16667 | 6 | 216.6667 | 0.027778 | https://youtu.be/T0Xn-92j2EU | Planned |  |  | 42
43 | 15 | PS-03 | Probability & Statistics | 3 | Grinstead & Snell, Intro to Probability §4.1 Bayes' Formula | Bayes' theorem, visually: updating beliefs with evidence | Explainer | 10-12 min | PS-02 | Medium | 70 | 5 | 2 | The better way to do statistics ¦ Bayesian #1 | Very Normal | 132000 | 434000 | 3.2879 | 2 | 217000 | 1.6439 | https://youtu.be/3jP4H0kjtng | Planned |  |  | 43
44 | 15 | XC-03 | Cross-course | 3 | History-of-an-idea format | How Bayes' theorem was lost, found and started a 200-year argument | History of an idea | 15-20 min | PS-03 | Medium | 70 | 5 | 2 | The better way to do statistics ¦ Bayesian #1 | Very Normal | 132000 | 434000 | 3.2879 | 2 | 217000 | 1.6439 | https://youtu.be/3jP4H0kjtng | Planned |  |  | 44
45 | 15 | LA-20 | Linear Algebra | 20 | Hefferon, Linear Algebra §5.II.3 Eigenvalues and Eigenvectors | Eigenvectors and eigenvalues: the directions a matrix doesn't turn | Explainer | 10-12 min | LA-14 | Medium | 63 | 13 | 0 | What is an Eigenvector? | Leios | 99100 | 494000 | 4.9849 | 10 | 49400 | 0.49849 | https://youtu.be/ue3yoeZvt8E | Planned |  |  | 45
46 | 16 | XC-01 | Cross-course | 1 | Dr Sean "5 levels" format | Eigenvectors in 5 levels: high school to research | 5 levels | 10-12 min | LA-20 | High | 13 | 8 | 6 | Dividing by Zero in Five Levels -- Elementary to Math Major | Dr Sean | 22900 | 1200000 | 52.4017 | 2 | 600000 | 26.2009 | https://youtu.be/dHdg1yn1SgE | Planned |  |  | 46
47 | 16 | PS-04 | Probability & Statistics | 4 | Grinstead & Snell, Intro to Probability §4.1 Bayes (applications) | The medical-test paradox: why a positive test might mean you're fine | Explainer | 6-8 min | PS-03 | Low | 4 | 0 | 0 | False Positives vs. False Negatives in Science and Statistics (Type 1 and Type 2 Error) | Galak Breaks It Down | 26600 | 20000 | 0.75188 | 5 | 4000 | 0.15038 | https://youtu.be/Zf1MLaWIOfQ | Planned |  |  | 47
48 | 16 | DE-20 | Differential Equations | 20 | Trench, Elementary Differential Equations §8.6-8.7 Convolution and Impulse | Convolution and the Dirac delta: what a hammer blow does to a system | Explainer | 10-12 min | DE-18 | High | 44 | 5 | 0 | Convolution Explained Visually — Finally Understand the Math! | Mathspark8 | 7140 | 83000 | 11.6246 | 0.25 | 332000 | 46.4986 | https://youtu.be/F4Edh2S_I-Q | Planned |  |  | 48
49 | 17 | PS-05 | Probability & Statistics | 5 | Grinstead & Snell, Intro to Probability §3.1 Permutations and Combinations | Counting without listing: permutations and combinations in pictures | Explainer | 8-10 min | PS-01 | High | 61 | 3 | 1 | 0! = 1 Explained in 5 Levels from Counting to Math Major | Dr Sean | 22900 | 443000 | 19.345 | 2 | 221500 | 9.6725 | https://youtu.be/_v9xa2ohzIk | Planned |  |  | 49
50 | 17 | LA-21 | Linear Algebra | 21 | Hefferon, Linear Algebra §5.II.3 Eigenvalues and Eigenvectors | How to actually find eigenvalues (characteristic polynomial, visualised) | Explainer | 8-10 min | LA-20 | Medium | 8 | 1 | 0 | 8: Eigenvalue Method for Systems - Dissecting Differential Equations | Mu Prime Math | 52900 | 99000 | 1.8715 | 6 | 16500 | 0.31191 | https://youtu.be/E0YUvCqhr-c | Planned |  |  | 50
51 | 17 | PS-06 | Probability & Statistics | 6 | Grinstead & Snell, Intro to Probability §5.1 Discrete Distributions | Random variables and distributions: from a coin to a histogram | Explainer | 8-10 min | PS-01 | High | 82 | 5 | 4 | Random Variables and Probability Distributions | Dr Nic's Maths and Stats | 128000 | 489000 | 3.8203 | 12 | 40750 | 0.31836 | https://youtu.be/lHCpYeFvTs0 | Planned |  |  | 51
52 | 18 | DE-21 | Differential Equations | 21 | Trench, Elementary Differential Equations §10.1-10.3 Linear Systems of DEs | Systems of DEs: when two quantities depend on each other | Explainer | 8-10 min | DE-11, LA-20 | Medium | 20 | 2 | 1 | Systems of linear first-order odes ¦ Lecture 39 ¦ Differential Equations for Engineers | Jeffrey Chasnov | 102000 | 256000 | 2.5098 | 7 | 36571.4286 | 0.35854 | https://youtu.be/ASYKt0P7I9c | Planned |  |  | 52
53 | 18 | PS-07 | Probability & Statistics | 7 | Grinstead & Snell, Intro to Probability §6.1 Expected Value | Expected value: the number you'd get on average (and when it lies) | Explainer | 8-10 min | PS-06 | Medium | 20 | 1 | 0 | Expected Value Explained Intuitively | Galak Breaks It Down | 26600 | 67000 | 2.5188 | 5 | 13400 | 0.50376 | https://youtu.be/nKBun2JmqlE | Planned |  |  | 53
54 | 18 | LA-22 | Linear Algebra | 22 | Hefferon, Linear Algebra §5.II.2 Diagonalizability | Diagonalisation: why A = PDP⁻¹ makes everything easy | Explainer | 10-12 min | LA-21 | Medium | 11 | 3 | 0 | Unitary Diagonalization - The Whole Enchilada! | Andrew Misseldine | 5670 | 10000 | 1.7637 | 6 | 1666.6667 | 0.29394 | https://youtu.be/hvGf1X-p6PM | Planned |  |  | 54
55 | 19 | PS-08 | Probability & Statistics | 8 | Grinstead & Snell, Intro to Probability §6.2 Variance | Variance and standard deviation: why we square the differences | Explainer | 8-10 min | PS-07 | High | 146 | 9 | 3 | Covariance and correlation | Ben Lambert | 149000 | 708000 | 4.7517 | 13 | 54461.5385 | 0.36551 | https://youtu.be/KDw3hC2YNFc | Planned |  |  | 55
56 | 19 | DE-22 | Differential Equations | 22 | Trench, Elementary Differential Equations §10.4 Constant Coefficient Systems I | Phase portraits I: real eigenvalues (saddles, sources, sinks) | Explainer | 10-12 min | DE-21 | Medium | 6 | 2 | 0 | Phase portraits of linear systems ¦ Lecture 42 ¦ Differential Equations for Engineers | Jeffrey Chasnov | 102000 | 119000 | 1.1667 | 7 | 17000 | 0.16667 | https://youtu.be/UO_dgXa5szg | Planned |  |  | 56
57 | 19 | PS-09 | Probability & Statistics | 9 | OpenIntro Statistics (4e) §4.3 Binomial Distribution | The binomial distribution: every yes/no experiment at once | Explainer | 8-10 min | PS-06 | Low | 17 | 0 | 0 | Understanding the Binomial Probability Distribution - statistics help | Dr Nic's Maths and Stats | 128000 | 54000 | 0.42188 | 7 | 7714.2857 | 0.060268 | https://youtu.be/3EZbX2ftCUk | Planned |  |  | 57
58 | 20 | LA-23 | Linear Algebra | 23 | Hefferon, Linear Algebra §5.II Similarity | Matrix powers, Fibonacci and the closed form (diagonalisation in action) | Explainer | 8-10 min | LA-22 | High | 38 | 3 | 1 | One second to compute the largest Fibonacci number I can | Sheafification of G | 91100 | 918000 | 10.0768 | 2 | 459000 | 5.0384 | https://youtu.be/KzT9I1d-LlQ | Planned |  |  | 58
59 | 20 | PS-10 | Probability & Statistics | 10 | OpenIntro Statistics (4e) §4.5 Poisson Distribution | The Poisson distribution: counting rare events | Explainer | 8-10 min | PS-09 | Medium | 34 | 3 | 1 | 4. MLE Example: Poisson | Christina Knudson (Dr. Knudson) | 27600 | 74000 | 2.6812 | 9 | 8222.2222 | 0.29791 | https://youtu.be/n8YcOUZRZy8 | Planned |  |  | 59
60 | 20 | DE-23 | Differential Equations | 23 | Trench, Elementary Differential Equations §10.6 Constant Coefficient Systems III | Phase portraits II: complex eigenvalues (spirals and centres) | Explainer | 10-12 min | DE-22 | Medium | 7 | 2 | 1 | Phase portraits of linear systems ¦ Lecture 42 ¦ Differential Equations for Engineers | Jeffrey Chasnov | 102000 | 119000 | 1.1667 | 7 | 17000 | 0.16667 | https://youtu.be/UO_dgXa5szg | Planned |  |  | 60
61 | 21 | PS-11 | Probability & Statistics | 11 | OpenIntro Statistics (4e) §4.1 Normal Distribution | Where the bell curve comes from | Explainer | 10-12 min | PS-08 | High | 25 | 3 | 1 | Normal Distribution (PDF, CDF, PPF) in 3 Minutes | 3-Minute Data Science | 29900 | 193000 | 6.4548 | 3 | 64333.3333 | 2.1516 | https://youtu.be/3VYupIsbLlY | Planned |  |  | 61
62 | 21 | LA-24 | Linear Algebra | 24 | Hefferon, Linear Algebra Topic: Markov Chains | Markov chains with matrices: where does the system end up? | Explainer | 10-12 min | LA-22 | High | 49 | 9 | 4 | Markov Chains Clearly Explained! Part - 1 | Normalized Nerd | 139000 | 1900000 | 13.6691 | 5 | 380000 | 2.7338 | https://youtu.be/i3AkTO9HLXo | Planned |  |  | 62
63 | 21 | PS-12 | Probability & Statistics | 12 | Grinstead & Snell, Intro to Probability §8.1 Law of Large Numbers | The law of large numbers: why casinos always win | Explainer | 8-10 min | PS-07 | Low | 3 | 0 | 0 | The Law of Large Numbers | Christina Knudson (Dr. Knudson) | 27600 | 7700 | 0.27899 | 7 | 1100 | 0.039855 | https://youtu.be/FYRnJh4PH3E | Planned |  |  | 63
64 | 22 | DE-24 | Differential Equations | 24 | Lebl, Notes on Diffy Qs §8.1-8.2 Nonlinear Systems / Linearisation | Predator-prey and the pendulum: linearising nonlinear systems | Explainer | 10-12 min | DE-23 | High | 6 | 2 | 1 | Double pendulum ¦ Chaos ¦ Butterfly effect ¦ Computer simulation | Think Twice | 121000 | 3900000 | 32.2314 | 9 | 433333.3333 | 3.5813 | https://youtu.be/d0Z8wLLPNE0 | Planned |  |  | 64
65 | 22 | PS-13 | Probability & Statistics | 13 | Grinstead & Snell, Intro to Probability §9.1 Central Limit Theorem | The central limit theorem, visualised: why everything becomes normal | Explainer | 10-12 min | PS-11 | High | 18 | 2 | 1 | Terence Tao's Central Limit Theorem Proof, Double Factorials (!!) and the Moment Method #SoME3 | Prof Mihai Nica | 18000 | 117000 | 6.5 | 3 | 39000 | 2.1667 | https://youtu.be/oPQ4mNcqY7k | Planned |  |  | 65
66 | 22 | LA-25 | Linear Algebra | 25 | Hefferon, Linear Algebra Topic: Page Ranking | PageRank: the eigenvector that built Google | Explainer | 10-12 min | LA-24 | Medium | 18 | 0 | 1 | Google Colab for Python Beginners - Visually Explained | Visually Explained | 123000 | 109000 | 0.88618 | 0.67 | 162686.5672 | 1.3227 | https://youtu.be/5sgJsCah9bs | Planned |  |  | 66
67 | 23 | PS-14 | Probability & Statistics | 14 | Grinstead & Snell, Intro to Probability §11.1 Markov Chains | Markov chains explained: memoryless systems and where they settle | Explainer | 10-12 min | PS-02 | High | 49 | 9 | 4 | Markov Chains Clearly Explained! Part - 1 | Normalized Nerd | 139000 | 1900000 | 13.6691 | 5 | 380000 | 2.7338 | https://youtu.be/i3AkTO9HLXo | Planned |  |  | 67
68 | 23 | DE-25 | Differential Equations | 25 | Trench, Elementary Differential Equations §7.1-7.2 Series Solutions | Series solutions: when you can't solve it, approximate it | Explainer | 8-10 min | DE-12 | Medium | 30 | 1 | 0 | Solving ODEs by Series Solutions: Legendre's ODE | Faculty of Khan | 105000 | 203000 | 1.9333 | 10 | 20300 | 0.19333 | https://youtu.be/3e5BUrtUKZc | Planned |  |  | 68
69 | 23 | PS-15 | Probability & Statistics | 15 | Grinstead & Snell, Intro to Probability §2.1 Simulation / Monte Carlo | Monte Carlo simulation: solving hard problems with random numbers | Explainer | 8-10 min | PS-12 | High | 35 | 7 | 3 | A Simple Solution for Really Hard Problems: Monte Carlo Simulation | RiskByNumbers | 21000 | 464000 | 22.0952 | 3 | 154666.6667 | 7.3651 | https://youtu.be/slbZ-SLpIgg | Planned |  |  | 69
70 | 24 | LA-26 | Linear Algebra | 26 | Hefferon, Linear Algebra §5.I Complex Vector Spaces | Complex eigenvalues mean rotation: the geometry nobody shows you | Explainer | 8-10 min | LA-21 | Low | 5 | 0 | 0 | systems with complex eigenvalues -- differential equations 23 | MathMajor | 49500 | 3800 | 0.076768 | 3 | 1266.6667 | 0.025589 | https://youtu.be/jTY32VgmWPI | Planned |  |  | 70
71 | 24 | PS-16 | Probability & Statistics | 16 | OpenIntro Statistics (4e) §1.3 Sampling Principles | Sampling methods: random, stratified, cluster (and what goes wrong) | Explainer | 6-8 min | None | Medium | 58 | 6 | 1 | Sampling: Simple Random, Convenience, systematic, cluster, stratified - Statistics Help | Dr Nic's Maths and Stats | 128000 | 1800000 | 14.0625 | 14 | 128571.4286 | 1.0045 | https://youtu.be/be9e-Q-jC-0 | Planned |  |  | 71
72 | 24 | DE-26 | Differential Equations | 26 | Trench, Elementary Differential Equations §11.2 Fourier Series I | Fourier series as a change of basis (the linear algebra view) | Explainer | 12-15 min | DE-11, LA-18 | High | 29 | 6 | 0 | Fourier Series Explained Visually — The Beauty of Mathematics | Mathspark8 | 7140 | 31000 | 4.3417 | 0.25 | 124000 | 17.3669 | https://youtu.be/eF2YEgipJTk | Planned |  |  | 72
73 | 25 | XC-02 | Cross-course | 2 | Abide By Reason "discovery" format | How Fourier discovered the Fourier series (and why nobody believed him) | History of an idea | 15-20 min | DE-26 | High | 113 | 21 | 4 | How Entropy Was Discovered | Abide By Reason | 130000 | 1200000 | 9.2308 | 0.25 | 4800000 | 36.9231 | https://youtu.be/WI0ZLkxJ6Zk | Planned |  |  | 73
74 | 25 | PS-17 | Probability & Statistics | 17 | OpenIntro Statistics (4e) §1.2 Data Basics | Types of data: nominal, ordinal, interval, ratio (and why it decides your test) | Explainer | 6-8 min | None | Medium | 8 | 1 | 1 | Types of Data: Nominal, Ordinal, Interval/Ratio - Statistics Help | Dr Nic's Maths and Stats | 128000 | 2100000 | 16.4062 | 14 | 150000 | 1.1719 | https://youtu.be/hZxnzfnt5v8 | Planned |  |  | 74
75 | 25 | LA-27 | Linear Algebra | 27 | Hefferon, Linear Algebra §3.II-III Symmetric matrices (Spectral Theorem) | The spectral theorem: why symmetric matrices are the nicest matrices | Explainer | 10-12 min | LA-22 | Medium | 38 | 1 | 0 | Visualize Spectral Decomposition ¦ SEE Matrix, Chapter 2 | Visual Kernel | 51500 | 172000 | 3.3398 | 4 | 43000 | 0.83495 | https://youtu.be/mhy-ZKSARxI | Planned |  |  | 75
76 | 26 | PS-18 | Probability & Statistics | 18 | OpenIntro Statistics (4e) §5.1 Point Estimates and Sampling Variability | Sampling distributions: the idea the whole of statistics rests on | Explainer | 10-12 min | PS-13 | Low | 16 | 0 | 0 | The standard error of the mean (SEM)¦ how to calculate and interpret ¦ SE vs SD | TileStats | 36000 | 12000 | 0.33333 | 5 | 2400 | 0.066667 | https://youtu.be/xmlmL1-4oPE | Planned |  |  | 76
77 | 26 | DE-27 | Differential Equations | 27 | Trench, Elementary Differential Equations §12.1 The Heat Equation | The heat equation: separation of variables from first principles | Explainer | 12-15 min | DE-26 | Medium | 17 | 3 | 0 | PDE 13 ¦ Wave equation: separation of variables | commutant | 43100 | 346000 | 8.0278 | 14 | 24714.2857 | 0.57342 | https://youtu.be/EJLympg3XMM | Planned |  |  | 77
78 | 26 | PS-19 | Probability & Statistics | 19 | OpenIntro Statistics (4e) §5.2 Confidence Intervals | Confidence intervals: what 95% really means | Explainer | 8-10 min | PS-18 | Medium | 70 | 4 | 1 | Understanding Confidence Intervals: Statistics Help | Dr Nic's Maths and Stats | 128000 | 2000000 | 15.625 | 13 | 153846.1538 | 1.2019 | https://youtu.be/tFWsuO9f74o | Planned |  |  | 78
79 | 27 | LA-28 | Linear Algebra | 28 | Hefferon, Linear Algebra Topic: Singular Value Decomposition | SVD explained visually: every matrix is rotate-stretch-rotate | Explainer | 12-15 min | LA-27 | High | 13 | 4 | 2 | What is the Singular Value Decomposition? | Stochastic | 2220 | 165000 | 74.3243 | 5 | 33000 | 14.8649 | https://youtu.be/CpD9XlTu3ys | Planned |  |  | 79
80 | 27 | PS-20 | Probability & Statistics | 20 | OpenIntro Statistics (4e) §5.3 Hypothesis Testing | Hypothesis testing step by step: null, alternative, decision | Explainer | 10-12 min | PS-19 | Medium | 51 | 2 | 1 | Hypothesis testing: step-by-step, p-value, t-test for difference of two means - Statistics Help | Dr Nic's Maths and Stats | 128000 | 989000 | 7.7266 | 14 | 70642.8571 | 0.5519 | https://youtu.be/0zZYBALbZgg | Planned |  |  | 80
81 | 27 | DE-28 | Differential Equations | 28 | Trench, Elementary Differential Equations §12.2 The Wave Equation | The wave equation: why a guitar string sounds the way it does | Explainer | 12-15 min | DE-27 | Medium | 21 | 7 | 0 | PDE 13 ¦ Wave equation: separation of variables | commutant | 43100 | 346000 | 8.0278 | 14 | 24714.2857 | 0.57342 | https://youtu.be/EJLympg3XMM | Planned |  |  | 81
82 | 28 | PS-21 | Probability & Statistics | 21 | OpenIntro Statistics (4e) §5.3 Hypothesis Testing (p-values) | What a p-value is (and the 3 things it isn't) | Explainer | 8-10 min | PS-20 | High | 41 | 6 | 3 | P-value in statistics: Understanding the p-value and what it tells us - Statistics Help | Dr Nic's Maths and Stats | 128000 | 1700000 | 13.2812 | 14 | 121428.5714 | 0.94866 | https://youtu.be/eyknGvncKLw | Planned |  |  | 82
83 | 28 | LA-29 | Linear Algebra | 29 | Hefferon, Linear Algebra Topic: SVD / Principal Component Analysis | PCA from scratch: the linear algebra behind dimensionality reduction | Explainer | 12-15 min | LA-28 | Medium | 22 | 5 | 0 | PCA : the math - step-by-step with a simple example | TileStats | 36000 | 164000 | 4.5556 | 5 | 32800 | 0.91111 | https://youtu.be/S51bTyIwxFs | Planned |  |  | 83
84 | 28 | PS-22 | Probability & Statistics | 22 | OpenIntro Statistics (4e) §7.1 t-distribution | The t-test and the t-distribution: small samples, honest uncertainty | Explainer | 8-10 min | PS-20 | Medium | 79 | 5 | 0 | Hypothesis testing: step-by-step, p-value, t-test for difference of two means - Statistics Help | Dr Nic's Maths and Stats | 128000 | 989000 | 7.7266 | 14 | 70642.8571 | 0.5519 | https://youtu.be/0zZYBALbZgg | Planned |  |  | 84
85 | 29 | DE-29 | Differential Equations | 29 | Trench, Elementary Differential Equations §12.3 Laplace's Equation | Laplace's equation and steady states: the smoothest function in the room | Explainer | 10-12 min | DE-27 | Low | 14 | 0 | 0 | Complex analysis: Harmonic functions | Richard E Borcherds | 83500 | 29000 | 0.34731 | 5 | 5800 | 0.069461 | https://youtu.be/NQFAxV6kdB8 | Planned |  |  | 85
86 | 29 | PS-23 | Probability & Statistics | 23 | OpenIntro Statistics (4e) §5.3 Decision Errors / §7.4 Power | Type I and Type II errors, power: the four outcomes of every test | Explainer | 8-10 min | PS-20 | Low | 14 | 0 | 0 | Type 1 and Type 2 errors - Statistics Help | Dr Nic's Maths and Stats | 128000 | 83000 | 0.64844 | 7 | 11857.1429 | 0.092634 | https://youtu.be/edzQQFNzFjM | Planned |  |  | 86
87 | 29 | LA-30 | Linear Algebra | 30 | Hefferon, Linear Algebra §5.IV Jordan Form | When a matrix can't be diagonalised: Jordan form, gently | Explainer | 10-12 min | LA-22 | Medium | 11 | 1 | 0 | Why Some Matrices Cannot Be Diagonalized! 🤯 ¦ Eigenvalues, Eigenvectors & Jordan Form Explained | Mathspark8 | 7140 | 10000 | 1.4006 | 0.25 | 40000 | 5.6022 | https://youtu.be/DCoR7n5J_QM | Planned |  |  | 87
88 | 30 | PS-24 | Probability & Statistics | 24 | OpenIntro Statistics (4e) §7.5 ANOVA | ANOVA explained visually: comparing many means at once | Explainer | 10-12 min | PS-22 | High | 50 | 4 | 1 | Analysis of Variance (ANOVA) and F statistics .... MADE EASY!!! | Stats with Brian | 19200 | 166000 | 8.6458 | 2 | 83000 | 4.3229 | https://youtu.be/YllG5Cy6OFw | Planned |  |  | 88
89 | 30 | LA-31 | Linear Algebra | 31 | Hefferon, Linear Algebra §3.I Isomorphisms | Isomorphism: when two vector spaces are secretly the same | Explainer | 8-10 min | LA-11 | Low | 22 | 0 | 0 | Simplifying problems with isomorphisms, explained — Group Theory Ep. 2 | Nemean | 122000 | 54000 | 0.44262 | 1 | 54000 | 0.44262 | https://youtu.be/VZiLpYC0t5E | Planned |  |  | 89
90 | 30 | PS-25 | Probability & Statistics | 25 | OpenIntro Statistics (4e) §6.3-6.4 Chi-square | The chi-square test: are these categories independent? | Explainer | 8-10 min | PS-20 | Medium | 31 | 1 | 0 | The Chi-square test of independence VS homogeneity and goodness of fit | TileStats | 36000 | 40000 | 1.1111 | 5 | 8000 | 0.22222 | https://youtu.be/TyD-_1JUhxw | Planned |  |  | 90
91 | 31 | LA-32 | Linear Algebra | 32 | Hefferon, Linear Algebra §4.II Geometry of Determinants | Cramer's rule as geometry (why it works, not just how) | Explainer | 6-8 min | LA-14 | Low | 4 | 0 | 0 | Geometric Algebra in 2D - Linear Algebra and Cramer's Rule | Mathoma | 31100 | 22000 | 0.7074 | 10 | 2200 | 0.07074 | https://youtu.be/dnzUgDl43rQ | Planned |  |  | 91
92 | 31 | PS-26 | Probability & Statistics | 26 | OpenIntro Statistics (4e) Ch.5-7 (summary) | Which statistical test should I use? A visual decision tree | Explainer | 8-10 min | PS-20…PS-25 | Medium | 2 | 1 | 1 | Statistical Tests: Choosing which statistical test to use | Dr Nic's Maths and Stats | 128000 | 1800000 | 14.0625 | 14 | 128571.4286 | 1.0045 | https://youtu.be/rulIUAN0U3w | Planned |  |  | 92
93 | 31 | LA-33 | Linear Algebra | 33 | Hefferon, Linear Algebra Topic: Geometry of Linear Maps | Shear, rotation, reflection, projection: the 2×2 matrix zoo | Explainer | 8-10 min | LA-07 | Medium | 42 | 4 | 0 | 3D Rotations in General: Rodrigues Rotation Formula and Quaternion Exponentials | Mathoma | 31100 | 115000 | 3.6977 | 10 | 11500 | 0.36977 | https://youtu.be/q-ESzg03mQc | Planned |  |  | 93
94 | 32 | PS-27 | Probability & Statistics | 27 | OpenIntro Statistics (4e) §8.1-8.2 Linear Regression | Linear regression explained visually: the line that minimises squares | Explainer | 10-12 min | PS-08, LA-19 | High | 185 | 18 | 4 | Linear Regression in 3 Minutes | 3-Minute Data Science | 29900 | 456000 | 15.2508 | 4 | 114000 | 3.8127 | https://youtu.be/3dhcmeOTZ_Q | Planned |  |  | 94
95 | 32 | LA-34 | Linear Algebra | 34 | Hefferon, Linear Algebra §3.VI Projection (applications) | Why the normal equations work: least squares in one picture | Explainer | 6-8 min | LA-19 | High | 185 | 18 | 4 | Linear Regression in 3 Minutes | 3-Minute Data Science | 29900 | 456000 | 15.2508 | 4 | 114000 | 3.8127 | https://youtu.be/3dhcmeOTZ_Q | Planned |  |  | 95
96 | 32 | PS-28 | Probability & Statistics | 28 | OpenIntro Statistics (4e) §8.1 Correlation | Correlation and R²: what the numbers measure and what they miss | Explainer | 8-10 min | PS-27 | Medium | 93 | 11 | 2 | Covariance and correlation | Ben Lambert | 149000 | 708000 | 4.7517 | 13 | 54461.5385 | 0.36551 | https://youtu.be/KDw3hC2YNFc | Planned |  |  | 96
97 | 33 | LA-35 | Linear Algebra | 35 | Hefferon, Linear Algebra Topic: Dimensional Analysis / Orthogonal matrices | Orthogonal matrices: transformations that preserve length | Explainer | 6-8 min | LA-18 | Medium | 6 | 1 | 0 | Orthogonal matrices ¦ Lecture 7 ¦ Matrix Algebra for Engineers | Jeffrey Chasnov | 102000 | 143000 | 1.402 | 8 | 17875 | 0.17525 | https://youtu.be/IGBm-gZryVI | Planned |  |  | 97
98 | 33 | PS-29 | Probability & Statistics | 29 | Downey, Think Stats §8 Estimation (MLE) | Maximum likelihood estimation: the intuition behind fitting | Explainer | 10-12 min | PS-06, Calculus 1 | High | 47 | 16 | 5 | 1. Maximum Likelihood Estimation Basics | Christina Knudson (Dr. Knudson) | 27600 | 327000 | 11.8478 | 9 | 36333.3333 | 1.3164 | https://youtu.be/93fPFOf547Q | Planned |  |  | 98
99 | 33 | PS-30 | Probability & Statistics | 30 | OpenIntro Statistics (4e) §9.5 Logistic Regression | Logistic regression: how to predict a yes/no | Explainer | 10-12 min | PS-27 | High | 35 | 2 | 1 | Logistic Regression in 3 Minutes | 3-Minute Data Science | 29900 | 245000 | 8.194 | 4 | 61250 | 2.0485 | https://youtu.be/EKm0spFxFG4 | Planned |  |  | 99
100 | 34 | PS-31 | Probability & Statistics | 31 | OpenIntro + Grinstead & Snell (whole) | ALL of Probability & Statistics in 10 minutes | Anchor (ALL of…) | 10 min | PS-01…PS-30 | Medium | 4 | 1 | 0 | The Map of Statistics (all of Statistics in 15 mins!) | Meerkat Statistics | 12100 | 31000 | 2.562 | 4 | 7750 | 0.6405 | https://youtu.be/Xy4CLCpqUB4 | Planned |  |  | 100
Yellow cells (Status, Publish date) are yours to edit. Week = Order / 3 rounded up (3 videos a week). Views / subs is a live formula.

## Schedule
Week | Phase | Video 1 | Video 2 | Video 3
1 | Phase 1: LA + DE explainers | LA-01 What a system of linear equations really is (and why 3 pictures beat 3 formulas) | DE-01 What is a differential equation? (and why physics is written in them) | LA-02 Gaussian elimination: the algorithm, visualised row by row
2 | Phase 1: LA + DE explainers | DE-02 Slope fields: seeing every solution at once | LA-03 Row echelon form explained: what the zeros are telling you | DE-03 Separable equations: the first trick everyone learns, explained properly
3 | Phase 1: LA + DE explainers | LA-04 Why solution sets are lines, planes and points (particular + homogeneous) | DE-04 Integrating factors: where that mysterious e^∫p comes from | LA-05 Vectors are not arrows: three ways to think about a vector
4 | Phase 1: LA + DE explainers | DE-05 Existence and uniqueness, intuitively: when does a DE have one answer? | LA-06 The dot product explained visually (projection, angle, work) | DE-06 Exact equations and the hidden potential function
5 | Phase 1: LA + DE explainers | LA-07 What a matrix really does: matrices as transformations | DE-07 Exponential growth and decay: the DE behind every population curve | LA-08 Why matrix multiplication is defined like that
6 | Phase 1: LA + DE explainers | DE-08 Newton's law of cooling and the mixing-tank problem, animated | LA-09 Span: everywhere your vectors can reach | DE-09 The phase line: stability without solving anything
7 | Phase 1: LA + DE explainers | LA-10 Linear independence: when is a vector redundant? | DE-10 Euler's method to Runge-Kutta: how computers solve DEs | LA-11 Basis and dimension: choosing your coordinate system
8 | Phase 1: LA + DE explainers | DE-11 Second-order linear DEs: why solutions form a 2D space | LA-12 Rank and nullity: what a matrix destroys and what it keeps | DE-12 The characteristic equation: three cases, three pictures
9 | Phase 1: LA anchor + explainers | LA-36 ALL of Linear Algebra in 8 minutes | LA-13 The inverse matrix: undoing a transformation (and when you can't) | DE-13 The mass on a spring: damping, visualised
10 | Phase 2: LA + DE explainers | LA-14 Why is the determinant like that? (area, volume and sign) | DE-14 Forcing terms and undetermined coefficients: guessing with a method | LA-15 Cofactor expansion without tears: where the formula comes from
11 | Phase 2: LA + DE explainers | DE-15 Resonance: why bridges and wine glasses break | LA-16 Change of basis: the same vector in two languages | DE-16 Variation of parameters, demystified
12 | Phase 2: LA + DE explainers | LA-17 Orthogonal projection: the closest point and why it matters | DE-17 The Laplace transform, visually: what it does to a function | LA-18 Gram-Schmidt in 3D: building an orthonormal basis step by step
13 | Phase 2: DE anchor; stats lane opens | DE-18 Solving differential equations with Laplace: turning calculus into algebra | DE-30 ALL of Differential Equations in 10 minutes | PS-01 What probability actually is: three interpretations, one set of rules
14 | Phase 3: Stats + remaining LA/DE | LA-19 Least squares explained visually: regression is projection | PS-02 Conditional probability: why your intuition fails (and how to fix it) | DE-19 Step functions and switches: Laplace for piecewise forcing
15 | Phase 3: Stats + remaining LA/DE | PS-03 Bayes' theorem, visually: updating beliefs with evidence | XC-03 How Bayes' theorem was lost, found and started a 200-year argument | LA-20 Eigenvectors and eigenvalues: the directions a matrix doesn't turn
16 | Phase 3: Stats + remaining LA/DE | XC-01 Eigenvectors in 5 levels: high school to research | PS-04 The medical-test paradox: why a positive test might mean you're fine | DE-20 Convolution and the Dirac delta: what a hammer blow does to a system
17 | Phase 3: Stats + remaining LA/DE | PS-05 Counting without listing: permutations and combinations in pictures | LA-21 How to actually find eigenvalues (characteristic polynomial, visualised) | PS-06 Random variables and distributions: from a coin to a histogram
18 | Phase 3: Stats + remaining LA/DE | DE-21 Systems of DEs: when two quantities depend on each other | PS-07 Expected value: the number you'd get on average (and when it lies) | LA-22 Diagonalisation: why A = PDP⁻¹ makes everything easy
19 | Phase 3: Stats + remaining LA/DE | PS-08 Variance and standard deviation: why we square the differences | DE-22 Phase portraits I: real eigenvalues (saddles, sources, sinks) | PS-09 The binomial distribution: every yes/no experiment at once
20 | Phase 3: Stats + remaining LA/DE | LA-23 Matrix powers, Fibonacci and the closed form (diagonalisation in action) | PS-10 The Poisson distribution: counting rare events | DE-23 Phase portraits II: complex eigenvalues (spirals and centres)
21 | Phase 3: Stats + remaining LA/DE | PS-11 Where the bell curve comes from | LA-24 Markov chains with matrices: where does the system end up? | PS-12 The law of large numbers: why casinos always win
22 | Phase 3: Stats + remaining LA/DE | DE-24 Predator-prey and the pendulum: linearising nonlinear systems | PS-13 The central limit theorem, visualised: why everything becomes normal | LA-25 PageRank: the eigenvector that built Google
23 | Phase 3: Stats + remaining LA/DE | PS-14 Markov chains explained: memoryless systems and where they settle | DE-25 Series solutions: when you can't solve it, approximate it | PS-15 Monte Carlo simulation: solving hard problems with random numbers
24 | Phase 3: Stats + remaining LA/DE | LA-26 Complex eigenvalues mean rotation: the geometry nobody shows you | PS-16 Sampling methods: random, stratified, cluster (and what goes wrong) | DE-26 Fourier series as a change of basis (the linear algebra view)
25 | Phase 3: Stats + remaining LA/DE | XC-02 How Fourier discovered the Fourier series (and why nobody believed him) | PS-17 Types of data: nominal, ordinal, interval, ratio (and why it decides your test) | LA-27 The spectral theorem: why symmetric matrices are the nicest matrices
26 | Phase 3: Stats + remaining LA/DE | PS-18 Sampling distributions: the idea the whole of statistics rests on | DE-27 The heat equation: separation of variables from first principles | PS-19 Confidence intervals: what 95% really means
27 | Phase 3: Stats + remaining LA/DE | LA-28 SVD explained visually: every matrix is rotate-stretch-rotate | PS-20 Hypothesis testing step by step: null, alternative, decision | DE-28 The wave equation: why a guitar string sounds the way it does
28 | Phase 3: Stats + remaining LA/DE | PS-21 What a p-value is (and the 3 things it isn't) | LA-29 PCA from scratch: the linear algebra behind dimensionality reduction | PS-22 The t-test and the t-distribution: small samples, honest uncertainty
29 | Phase 3: Stats + remaining LA/DE | DE-29 Laplace's equation and steady states: the smoothest function in the room | PS-23 Type I and Type II errors, power: the four outcomes of every test | LA-30 When a matrix can't be diagonalised: Jordan form, gently
30 | Phase 3: Stats + remaining LA/DE | PS-24 ANOVA explained visually: comparing many means at once | LA-31 Isomorphism: when two vector spaces are secretly the same | PS-25 The chi-square test: are these categories independent?
31 | Phase 3: Stats + remaining LA/DE | LA-32 Cramer's rule as geometry (why it works, not just how) | PS-26 Which statistical test should I use? A visual decision tree | LA-33 Shear, rotation, reflection, projection: the 2×2 matrix zoo
32 | Phase 3: Stats + remaining LA/DE | PS-27 Linear regression explained visually: the line that minimises squares | LA-34 Why the normal equations work: least squares in one picture | PS-28 Correlation and R²: what the numbers measure and what they miss
33 | Phase 3: Stats + remaining LA/DE | LA-35 Orthogonal matrices: transformations that preserve length | PS-29 Maximum likelihood estimation: the intuition behind fitting | PS-30 Logistic regression: how to predict a yes/no
34 | Phase 3: Stats anchor | PS-31 ALL of Probability & Statistics in 10 minutes

## By Course
Course | Playlist # | Code | Working title | Source section | Format | Length | Prerequisites | Demand signal | Production order
Linear Algebra | 1 | LA-01 | What a system of linear equations really is (and why 3 pictures beat 3 formulas) | Hefferon, Linear Algebra §1.I.1 Gauss's Method | Explainer | 6-8 min | None | High | 1
Linear Algebra | 2 | LA-02 | Gaussian elimination: the algorithm, visualised row by row | Hefferon, Linear Algebra §1.I.1 Gauss's Method | Explainer | 8-10 min | LA-01 | Medium | 3
Linear Algebra | 3 | LA-03 | Row echelon form explained: what the zeros are telling you | Hefferon, Linear Algebra §1.III Reduced Echelon Form | Explainer | 6-8 min | LA-02 | Medium | 5
Linear Algebra | 4 | LA-04 | Why solution sets are lines, planes and points (particular + homogeneous) | Hefferon, Linear Algebra §1.I.3 General = Particular + Homogeneous | Explainer | 6-8 min | LA-03 | Low | 7
Linear Algebra | 5 | LA-05 | Vectors are not arrows: three ways to think about a vector | Hefferon, Linear Algebra §1.II Linear Geometry of n-Space | Explainer | 6-8 min | None | Low | 9
Linear Algebra | 6 | LA-06 | The dot product explained visually (projection, angle, work) | Hefferon, Linear Algebra §1.II.2 Length and Angle Measures | Explainer | 8-10 min | LA-05 | Medium | 11
Linear Algebra | 7 | LA-07 | What a matrix really does: matrices as transformations | Hefferon, Linear Algebra §3.IV.2 Matrix Multiplication | Explainer | 8-10 min | LA-05 | High | 13
Linear Algebra | 8 | LA-08 | Why matrix multiplication is defined like that | Hefferon, Linear Algebra §3.IV.2 Matrix Multiplication | Explainer | 8-10 min | LA-07 | Low | 15
Linear Algebra | 9 | LA-09 | Span: everywhere your vectors can reach | Hefferon, Linear Algebra §2.I.2 Subspaces and Spanning Sets | Explainer | 6-8 min | LA-05 | Medium | 17
Linear Algebra | 10 | LA-10 | Linear independence: when is a vector redundant? | Hefferon, Linear Algebra §2.II Linear Independence | Explainer | 6-8 min | LA-09 | Medium | 19
Linear Algebra | 11 | LA-11 | Basis and dimension: choosing your coordinate system | Hefferon, Linear Algebra §2.III Basis and Dimension | Explainer | 8-10 min | LA-10 | Medium | 21
Linear Algebra | 12 | LA-12 | Rank and nullity: what a matrix destroys and what it keeps | Hefferon, Linear Algebra §3.II Homomorphisms (rank, nullity) | Explainer | 8-10 min | LA-11 | Medium | 23
Linear Algebra | 13 | LA-13 | The inverse matrix: undoing a transformation (and when you can't) | Hefferon, Linear Algebra §3.IV.4 Inverses | Explainer | 8-10 min | LA-07 | Medium | 26
Linear Algebra | 14 | LA-14 | Why is the determinant like that? (area, volume and sign) | Hefferon, Linear Algebra §4.I-II Determinants | Explainer | 10-12 min | LA-07 | High | 28
Linear Algebra | 15 | LA-15 | Cofactor expansion without tears: where the formula comes from | Hefferon, Linear Algebra §4.III Laplace's Formula | Explainer | 8-10 min | LA-14 | Low | 30
Linear Algebra | 16 | LA-16 | Change of basis: the same vector in two languages | Hefferon, Linear Algebra §3.V Change of Basis | Explainer | 10-12 min | LA-11 | Low | 32
Linear Algebra | 17 | LA-17 | Orthogonal projection: the closest point and why it matters | Hefferon, Linear Algebra §3.VI.1 Orthogonal Projection | Explainer | 8-10 min | LA-06 | High | 34
Linear Algebra | 18 | LA-18 | Gram-Schmidt in 3D: building an orthonormal basis step by step | Hefferon, Linear Algebra §3.VI.2 Gram-Schmidt | Explainer | 8-10 min | LA-17 | High | 36
Linear Algebra | 19 | LA-19 | Least squares explained visually: regression is projection | Hefferon, Linear Algebra Topic: Line of Best Fit | Explainer | 10-12 min | LA-17 | Medium | 40
Linear Algebra | 20 | LA-20 | Eigenvectors and eigenvalues: the directions a matrix doesn't turn | Hefferon, Linear Algebra §5.II.3 Eigenvalues and Eigenvectors | Explainer | 10-12 min | LA-14 | Medium | 45
Linear Algebra | 21 | LA-21 | How to actually find eigenvalues (characteristic polynomial, visualised) | Hefferon, Linear Algebra §5.II.3 Eigenvalues and Eigenvectors | Explainer | 8-10 min | LA-20 | Medium | 50
Linear Algebra | 22 | LA-22 | Diagonalisation: why A = PDP⁻¹ makes everything easy | Hefferon, Linear Algebra §5.II.2 Diagonalizability | Explainer | 10-12 min | LA-21 | Medium | 54
Linear Algebra | 23 | LA-23 | Matrix powers, Fibonacci and the closed form (diagonalisation in action) | Hefferon, Linear Algebra §5.II Similarity | Explainer | 8-10 min | LA-22 | High | 58
Linear Algebra | 24 | LA-24 | Markov chains with matrices: where does the system end up? | Hefferon, Linear Algebra Topic: Markov Chains | Explainer | 10-12 min | LA-22 | High | 62
Linear Algebra | 25 | LA-25 | PageRank: the eigenvector that built Google | Hefferon, Linear Algebra Topic: Page Ranking | Explainer | 10-12 min | LA-24 | Medium | 66
Linear Algebra | 26 | LA-26 | Complex eigenvalues mean rotation: the geometry nobody shows you | Hefferon, Linear Algebra §5.I Complex Vector Spaces | Explainer | 8-10 min | LA-21 | Low | 70
Linear Algebra | 27 | LA-27 | The spectral theorem: why symmetric matrices are the nicest matrices | Hefferon, Linear Algebra §3.II-III Symmetric matrices (Spectral Theorem) | Explainer | 10-12 min | LA-22 | Medium | 75
Linear Algebra | 28 | LA-28 | SVD explained visually: every matrix is rotate-stretch-rotate | Hefferon, Linear Algebra Topic: Singular Value Decomposition | Explainer | 12-15 min | LA-27 | High | 79
Linear Algebra | 29 | LA-29 | PCA from scratch: the linear algebra behind dimensionality reduction | Hefferon, Linear Algebra Topic: SVD / Principal Component Analysis | Explainer | 12-15 min | LA-28 | Medium | 83
Linear Algebra | 30 | LA-30 | When a matrix can't be diagonalised: Jordan form, gently | Hefferon, Linear Algebra §5.IV Jordan Form | Explainer | 10-12 min | LA-22 | Medium | 87
Linear Algebra | 31 | LA-31 | Isomorphism: when two vector spaces are secretly the same | Hefferon, Linear Algebra §3.I Isomorphisms | Explainer | 8-10 min | LA-11 | Low | 89
Linear Algebra | 32 | LA-32 | Cramer's rule as geometry (why it works, not just how) | Hefferon, Linear Algebra §4.II Geometry of Determinants | Explainer | 6-8 min | LA-14 | Low | 91
Linear Algebra | 33 | LA-33 | Shear, rotation, reflection, projection: the 2×2 matrix zoo | Hefferon, Linear Algebra Topic: Geometry of Linear Maps | Explainer | 8-10 min | LA-07 | Medium | 93
Linear Algebra | 34 | LA-34 | Why the normal equations work: least squares in one picture | Hefferon, Linear Algebra §3.VI Projection (applications) | Explainer | 6-8 min | LA-19 | High | 95
Linear Algebra | 35 | LA-35 | Orthogonal matrices: transformations that preserve length | Hefferon, Linear Algebra Topic: Dimensional Analysis / Orthogonal matrices | Explainer | 6-8 min | LA-18 | Medium | 97
Linear Algebra | 36 | LA-36 | ALL of Linear Algebra in 8 minutes | Hefferon (whole book) | Anchor (ALL of…) | 8 min | LA-01…LA-35 | High | 25
Differential Equations | 1 | DE-01 | What is a differential equation? (and why physics is written in them) | Trench, Elementary Differential Equations §1.2 Basic Concepts | Explainer | 6-8 min | Calculus 1 | Medium | 2
Differential Equations | 2 | DE-02 | Slope fields: seeing every solution at once | Trench, Elementary Differential Equations §1.3 Direction Fields | Explainer | 8-10 min | DE-01 | Medium | 4
Differential Equations | 3 | DE-03 | Separable equations: the first trick everyone learns, explained properly | Trench, Elementary Differential Equations §2.2 Separable Equations | Explainer | 8-10 min | DE-01 | Low | 6
Differential Equations | 4 | DE-04 | Integrating factors: where that mysterious e^∫p comes from | Trench, Elementary Differential Equations §2.1 Linear First Order | Explainer | 8-10 min | DE-03 | Medium | 8
Differential Equations | 5 | DE-05 | Existence and uniqueness, intuitively: when does a DE have one answer? | Trench, Elementary Differential Equations §2.3 Existence and Uniqueness | Explainer | 8-10 min | DE-02 | Medium | 10
Differential Equations | 6 | DE-06 | Exact equations and the hidden potential function | Trench, Elementary Differential Equations §2.5 Exact Equations | Explainer | 8-10 min | DE-04 | Low | 12
Differential Equations | 7 | DE-07 | Exponential growth and decay: the DE behind every population curve | Trench, Elementary Differential Equations §4.1 Growth and Decay | Explainer | 6-8 min | DE-03 | Medium | 14
Differential Equations | 8 | DE-08 | Newton's law of cooling and the mixing-tank problem, animated | Trench, Elementary Differential Equations §4.2 Cooling and Mixing | Explainer | 8-10 min | DE-04 | Medium | 16
Differential Equations | 9 | DE-09 | The phase line: stability without solving anything | Trench, Elementary Differential Equations §4.4 Autonomous Second Order / Lebl, Notes on Diffy Qs §1.6 | Explainer | 8-10 min | DE-02 | Medium | 18
Differential Equations | 10 | DE-10 | Euler's method to Runge-Kutta: how computers solve DEs | Trench, Elementary Differential Equations §3.1-3.3 Numerical Methods | Explainer | 10-12 min | DE-02 | Medium | 20
Differential Equations | 11 | DE-11 | Second-order linear DEs: why solutions form a 2D space | Trench, Elementary Differential Equations §5.1 Homogeneous Linear Equations | Explainer | 8-10 min | DE-04, LA-11 | Medium | 22
Differential Equations | 12 | DE-12 | The characteristic equation: three cases, three pictures | Trench, Elementary Differential Equations §5.2 Constant Coefficient Homogeneous | Explainer | 10-12 min | DE-11 | Low | 24
Differential Equations | 13 | DE-13 | The mass on a spring: damping, visualised | Trench, Elementary Differential Equations §6.1 Spring Problems | Explainer | 10-12 min | DE-12 | Medium | 27
Differential Equations | 14 | DE-14 | Forcing terms and undetermined coefficients: guessing with a method | Trench, Elementary Differential Equations §5.3-5.4 Nonhomogeneous / Undetermined Coefficients | Explainer | 8-10 min | DE-12 | High | 29
Differential Equations | 15 | DE-15 | Resonance: why bridges and wine glasses break | Trench, Elementary Differential Equations §6.1 Forced Oscillation | Explainer | 8-10 min | DE-13 | Low | 31
Differential Equations | 16 | DE-16 | Variation of parameters, demystified | Trench, Elementary Differential Equations §5.7 Variation of Parameters | Explainer | 8-10 min | DE-14 | Low | 33
Differential Equations | 17 | DE-17 | The Laplace transform, visually: what it does to a function | Trench, Elementary Differential Equations §8.1 Introduction to Laplace Transform | Explainer | 10-12 min | DE-12 | High | 35
Differential Equations | 18 | DE-18 | Solving differential equations with Laplace: turning calculus into algebra | Trench, Elementary Differential Equations §8.3 Solution of IVPs | Explainer | 10-12 min | DE-17 | Medium | 37
Differential Equations | 19 | DE-19 | Step functions and switches: Laplace for piecewise forcing | Trench, Elementary Differential Equations §8.4-8.5 Unit Step Functions | Explainer | 8-10 min | DE-18 | Low | 42
Differential Equations | 20 | DE-20 | Convolution and the Dirac delta: what a hammer blow does to a system | Trench, Elementary Differential Equations §8.6-8.7 Convolution and Impulse | Explainer | 10-12 min | DE-18 | High | 48
Differential Equations | 21 | DE-21 | Systems of DEs: when two quantities depend on each other | Trench, Elementary Differential Equations §10.1-10.3 Linear Systems of DEs | Explainer | 8-10 min | DE-11, LA-20 | Medium | 52
Differential Equations | 22 | DE-22 | Phase portraits I: real eigenvalues (saddles, sources, sinks) | Trench, Elementary Differential Equations §10.4 Constant Coefficient Systems I | Explainer | 10-12 min | DE-21 | Medium | 56
Differential Equations | 23 | DE-23 | Phase portraits II: complex eigenvalues (spirals and centres) | Trench, Elementary Differential Equations §10.6 Constant Coefficient Systems III | Explainer | 10-12 min | DE-22 | Medium | 60
Differential Equations | 24 | DE-24 | Predator-prey and the pendulum: linearising nonlinear systems | Lebl, Notes on Diffy Qs §8.1-8.2 Nonlinear Systems / Linearisation | Explainer | 10-12 min | DE-23 | High | 64
Differential Equations | 25 | DE-25 | Series solutions: when you can't solve it, approximate it | Trench, Elementary Differential Equations §7.1-7.2 Series Solutions | Explainer | 8-10 min | DE-12 | Medium | 68
Differential Equations | 26 | DE-26 | Fourier series as a change of basis (the linear algebra view) | Trench, Elementary Differential Equations §11.2 Fourier Series I | Explainer | 12-15 min | DE-11, LA-18 | High | 72
Differential Equations | 27 | DE-27 | The heat equation: separation of variables from first principles | Trench, Elementary Differential Equations §12.1 The Heat Equation | Explainer | 12-15 min | DE-26 | Medium | 77
Differential Equations | 28 | DE-28 | The wave equation: why a guitar string sounds the way it does | Trench, Elementary Differential Equations §12.2 The Wave Equation | Explainer | 12-15 min | DE-27 | Medium | 81
Differential Equations | 29 | DE-29 | Laplace's equation and steady states: the smoothest function in the room | Trench, Elementary Differential Equations §12.3 Laplace's Equation | Explainer | 10-12 min | DE-27 | Low | 85
Differential Equations | 30 | DE-30 | ALL of Differential Equations in 10 minutes | Trench (whole book) | Anchor (ALL of…) | 10 min | DE-01…DE-29 | Low | 38
Probability & Statistics | 1 | PS-01 | What probability actually is: three interpretations, one set of rules | Grinstead & Snell, Intro to Probability §1.2 Discrete Probability | Explainer | 8-10 min | None | Low | 39
Probability & Statistics | 2 | PS-02 | Conditional probability: why your intuition fails (and how to fix it) | Grinstead & Snell, Intro to Probability §4.1 Conditional Probability | Explainer | 8-10 min | PS-01 | Medium | 41
Probability & Statistics | 3 | PS-03 | Bayes' theorem, visually: updating beliefs with evidence | Grinstead & Snell, Intro to Probability §4.1 Bayes' Formula | Explainer | 10-12 min | PS-02 | Medium | 43
Probability & Statistics | 4 | PS-04 | The medical-test paradox: why a positive test might mean you're fine | Grinstead & Snell, Intro to Probability §4.1 Bayes (applications) | Explainer | 6-8 min | PS-03 | Low | 47
Probability & Statistics | 5 | PS-05 | Counting without listing: permutations and combinations in pictures | Grinstead & Snell, Intro to Probability §3.1 Permutations and Combinations | Explainer | 8-10 min | PS-01 | High | 49
Probability & Statistics | 6 | PS-06 | Random variables and distributions: from a coin to a histogram | Grinstead & Snell, Intro to Probability §5.1 Discrete Distributions | Explainer | 8-10 min | PS-01 | High | 51
Probability & Statistics | 7 | PS-07 | Expected value: the number you'd get on average (and when it lies) | Grinstead & Snell, Intro to Probability §6.1 Expected Value | Explainer | 8-10 min | PS-06 | Medium | 53
Probability & Statistics | 8 | PS-08 | Variance and standard deviation: why we square the differences | Grinstead & Snell, Intro to Probability §6.2 Variance | Explainer | 8-10 min | PS-07 | High | 55
Probability & Statistics | 9 | PS-09 | The binomial distribution: every yes/no experiment at once | OpenIntro Statistics (4e) §4.3 Binomial Distribution | Explainer | 8-10 min | PS-06 | Low | 57
Probability & Statistics | 10 | PS-10 | The Poisson distribution: counting rare events | OpenIntro Statistics (4e) §4.5 Poisson Distribution | Explainer | 8-10 min | PS-09 | Medium | 59
Probability & Statistics | 11 | PS-11 | Where the bell curve comes from | OpenIntro Statistics (4e) §4.1 Normal Distribution | Explainer | 10-12 min | PS-08 | High | 61
Probability & Statistics | 12 | PS-12 | The law of large numbers: why casinos always win | Grinstead & Snell, Intro to Probability §8.1 Law of Large Numbers | Explainer | 8-10 min | PS-07 | Low | 63
Probability & Statistics | 13 | PS-13 | The central limit theorem, visualised: why everything becomes normal | Grinstead & Snell, Intro to Probability §9.1 Central Limit Theorem | Explainer | 10-12 min | PS-11 | High | 65
Probability & Statistics | 14 | PS-14 | Markov chains explained: memoryless systems and where they settle | Grinstead & Snell, Intro to Probability §11.1 Markov Chains | Explainer | 10-12 min | PS-02 | High | 67
Probability & Statistics | 15 | PS-15 | Monte Carlo simulation: solving hard problems with random numbers | Grinstead & Snell, Intro to Probability §2.1 Simulation / Monte Carlo | Explainer | 8-10 min | PS-12 | High | 69
Probability & Statistics | 16 | PS-16 | Sampling methods: random, stratified, cluster (and what goes wrong) | OpenIntro Statistics (4e) §1.3 Sampling Principles | Explainer | 6-8 min | None | Medium | 71
Probability & Statistics | 17 | PS-17 | Types of data: nominal, ordinal, interval, ratio (and why it decides your test) | OpenIntro Statistics (4e) §1.2 Data Basics | Explainer | 6-8 min | None | Medium | 74
Probability & Statistics | 18 | PS-18 | Sampling distributions: the idea the whole of statistics rests on | OpenIntro Statistics (4e) §5.1 Point Estimates and Sampling Variability | Explainer | 10-12 min | PS-13 | Low | 76
Probability & Statistics | 19 | PS-19 | Confidence intervals: what 95% really means | OpenIntro Statistics (4e) §5.2 Confidence Intervals | Explainer | 8-10 min | PS-18 | Medium | 78
Probability & Statistics | 20 | PS-20 | Hypothesis testing step by step: null, alternative, decision | OpenIntro Statistics (4e) §5.3 Hypothesis Testing | Explainer | 10-12 min | PS-19 | Medium | 80
Probability & Statistics | 21 | PS-21 | What a p-value is (and the 3 things it isn't) | OpenIntro Statistics (4e) §5.3 Hypothesis Testing (p-values) | Explainer | 8-10 min | PS-20 | High | 82
Probability & Statistics | 22 | PS-22 | The t-test and the t-distribution: small samples, honest uncertainty | OpenIntro Statistics (4e) §7.1 t-distribution | Explainer | 8-10 min | PS-20 | Medium | 84
Probability & Statistics | 23 | PS-23 | Type I and Type II errors, power: the four outcomes of every test | OpenIntro Statistics (4e) §5.3 Decision Errors / §7.4 Power | Explainer | 8-10 min | PS-20 | Low | 86
Probability & Statistics | 24 | PS-24 | ANOVA explained visually: comparing many means at once | OpenIntro Statistics (4e) §7.5 ANOVA | Explainer | 10-12 min | PS-22 | High | 88
Probability & Statistics | 25 | PS-25 | The chi-square test: are these categories independent? | OpenIntro Statistics (4e) §6.3-6.4 Chi-square | Explainer | 8-10 min | PS-20 | Medium | 90
Probability & Statistics | 26 | PS-26 | Which statistical test should I use? A visual decision tree | OpenIntro Statistics (4e) Ch.5-7 (summary) | Explainer | 8-10 min | PS-20…PS-25 | Medium | 92
Probability & Statistics | 27 | PS-27 | Linear regression explained visually: the line that minimises squares | OpenIntro Statistics (4e) §8.1-8.2 Linear Regression | Explainer | 10-12 min | PS-08, LA-19 | High | 94
Probability & Statistics | 28 | PS-28 | Correlation and R²: what the numbers measure and what they miss | OpenIntro Statistics (4e) §8.1 Correlation | Explainer | 8-10 min | PS-27 | Medium | 96
Probability & Statistics | 29 | PS-29 | Maximum likelihood estimation: the intuition behind fitting | Downey, Think Stats §8 Estimation (MLE) | Explainer | 10-12 min | PS-06, Calculus 1 | High | 98
Probability & Statistics | 30 | PS-30 | Logistic regression: how to predict a yes/no | OpenIntro Statistics (4e) §9.5 Logistic Regression | Explainer | 10-12 min | PS-27 | High | 99
Probability & Statistics | 31 | PS-31 | ALL of Probability & Statistics in 10 minutes | OpenIntro + Grinstead & Snell (whole) | Anchor (ALL of…) | 10 min | PS-01…PS-30 | Medium | 100
Cross-course | 1 | XC-01 | Eigenvectors in 5 levels: high school to research | Dr Sean "5 levels" format | 5 levels | 10-12 min | LA-20 | High | 46
Cross-course | 2 | XC-02 | How Fourier discovered the Fourier series (and why nobody believed him) | Abide By Reason "discovery" format | History of an idea | 15-20 min | DE-26 | High | 73
Cross-course | 3 | XC-03 | How Bayes' theorem was lost, found and started a 200-year argument | History-of-an-idea format | History of an idea | 15-20 min | PS-03 | Medium | 44

## Progress
Progress
By status |  | By course | Videos | Published | By demand signal | Videos
Planned | 100 | Linear Algebra | 36 | 0 | High | 29
Scripted | 0 | Differential Equations | 30 | 0 | Medium | 49
Audio done | 0 | Probability & Statistics | 31 | 0 | Low | 22
Rendered | 0 | Cross-course | 3 | 0
Published | 0
Total | 100
Next up (first 5 not yet published)
LA-01 | What a system of linear equations really is (and why 3 pictures beat 3 formulas)
DE-01 | What is a differential equation? (and why physics is written in them)
LA-02 | Gaussian elimination: the algorithm, visualised row by row
DE-02 | Slope fields: seeing every solution at once
LA-03 | Row echelon form explained: what the zeros are telling you